## Read Me
Sciuro — UAT Test Tracker
Covers every module and functionality planned across the engineering, UI/UX, and automation discussions.
How to use this workbook
1. Work through the 'UAT Test Cases' sheet, module by module — the Phase column tells you roughly which build phase (from the v4 engineering plan) needs to be done before that test is runnable.
2. Set Status for each row using the dropdown: Not Tested, Pass, Fail, Blocked, N/A.
3. Record what actually happened in 'Actual Result / Notes' whenever it differs from Expected — this is especially useful for Fail and Blocked rows.
4. Fill in Tested By and Date Tested as you go.
5. Check the 'Summary Dashboard' sheet for a live pass/fail rollup by module — it recalculates automatically as you update Status.
Column reference
Test ID — short code, prefixed by module (e.g. PAR-03 = Parsing test #3)
Priority — Critical: must work correctly before anything else is trustworthy. High: core module correctness. Medium: UX polish and secondary paths. Low: nice-to-have / deferred scope.
Phase — approximate mapping back to the v4 engineering plan's milestones/phases (A0-A6, B1-B7, C1-C3, D1-D3) or the automation plan. A guide for sequencing, not a rigid contract.
Notes
This tracker assumes CIMB, Maybank, and BSN as the three bank sources, plus Touch 'n Go eWallet, GrabPay, Boost, and ShopeePay as the e-wallet sources, per the planning discussion.
Some tests (e.g. PAR-05, Bahasa Malaysia parsing) need you to actually trigger a real notification in that language/format — these can't be meaningfully faked, and are flagged High priority for exactly that reason.
Desktop Companion tests are Low priority since that scope was explicitly deferred in the engineering plan — include them for completeness, not urgency.

## Summary Dashboard
Sciuro UAT — Summary Dashboard
Recalculates automatically from the UAT Test Cases sheet as Status is updated.
Overall
Total Tests | Passed | Failed | Blocked | Not Tested | N/A | % Complete | % Pass Rate (of tested)
116 | 0 | 0 | 0 | 116 | 0 | 0% | 0%
By Module
Module | Total | Passed | Failed | Blocked | Not Tested | % Complete
Onboarding | 4 | 0 | 0 | 0 | 4 | 0%
Notification Capture | 6 | 0 | 0 | 0 | 6 | 0%
Parsing | 8 | 0 | 0 | 0 | 8 | 0%
Triage & Categorization | 6 | 0 | 0 | 0 | 6 | 0%
Transfer Detection | 6 | 0 | 0 | 0 | 6 | 0%
Physical Cash Wallet | 5 | 0 | 0 | 0 | 5 | 0%
E-Wallet Accounts | 5 | 0 | 0 | 0 | 5 | 0%
Recurring Obligations | 6 | 0 | 0 | 0 | 6 | 0%
Debt Ledger | 7 | 0 | 0 | 0 | 7 | 0%
Balance & Reconciliation | 4 | 0 | 0 | 0 | 4 | 0%
Investment / Gold | 5 | 0 | 0 | 0 | 5 | 0%
Budgeting | 5 | 0 | 0 | 0 | 5 | 0%
Audit Log | 5 | 0 | 0 | 0 | 5 | 0%
Cross-Module Cascades | 6 | 0 | 0 | 0 | 6 | 0%
Net Position | 3 | 0 | 0 | 0 | 3 | 0%
Review Inbox | 5 | 0 | 0 | 0 | 5 | 0%
Kanban Board | 5 | 0 | 0 | 0 | 5 | 0%
Home Dashboard | 5 | 0 | 0 | 0 | 5 | 0%
Navigation & UI Shell | 4 | 0 | 0 | 0 | 4 | 0%
Security | 5 | 0 | 0 | 0 | 5 | 0%
Empty/Loading States | 5 | 0 | 0 | 0 | 5 | 0%
Settings | 4 | 0 | 0 | 0 | 4 | 0%
Desktop Companion | 2 | 0 | 0 | 0 | 2 | 0%

## UAT Test Cases
Test ID | Module | Feature | Scenario | Preconditions | Test Steps | Expected Result | Priority | Phase | Status | Actual Result / Notes | Tested By | Date Tested
ONB-01 | Onboarding | First-run experience | Welcome & philosophy explainer displays | Fresh install, first launch | Install app and open for the first time | Welcome screens explain the minimal-interaction philosophy in plain language before any setup is requested | Medium | Milestone C | Not Tested
ONB-02 | Onboarding | Permission rationale | Notification access request shows rationale first | Onboarding in progress | Reach the notification-access step | A one-sentence explanation appears before the system permission dialog, not after | Critical | Milestone C | Not Tested
ONB-03 | Onboarding | Permission decline handling | Declining notification access is handled gracefully | On the permission step | Deny the notification access request | App does not crash; a clear path to grant access later from Settings is shown, no dead end | Critical | Milestone C | Not Tested
ONB-04 | Onboarding | Completion state | Onboarding ends on the correct Home empty state | Onboarding just completed, zero data | Complete all onboarding steps | Home screen shows the zero-transaction empty state, not an error or blank screen | Medium | Milestone C | Not Tested
NOT-01 | Notification Capture | Bank capture — CIMB | CIMB Clicks notification is captured | Notification access granted, CIMB Clicks installed | Trigger a real CIMB transaction notification | Notification is captured into the raw staging buffer within a few seconds | Critical | A2 | Not Tested
NOT-02 | Notification Capture | Bank capture — Maybank | Maybank2u notification is captured | Notification access granted, Maybank2u installed | Trigger a real Maybank2u transaction notification | Notification is captured into the raw staging buffer | Critical | A2 | Not Tested
NOT-03 | Notification Capture | Bank capture — BSN | BSN notification is captured | Notification access granted, BSN app installed | Trigger a real BSN transaction notification | Notification is captured into the raw staging buffer | Critical | A2 | Not Tested
NOT-04 | Notification Capture | Allowlist enforcement | Non-allowlisted app notifications are ignored | Any non-finance app installed (e.g. a messaging app) | Receive a notification from a non-allowlisted app | Notification is not captured, stored, or processed in any way | Critical | A2 | Not Tested
NOT-05 | Notification Capture | Background reliability | Capture works while app is backgrounded or killed | App backgrounded or force-closed | Trigger a bank notification while the app isn't in the foreground | Notification is still captured and later reflected in the transaction list once opened | Critical | A2 | Not Tested
NOT-06 | Notification Capture | Proactive app detection | New finance app install triggers a suggestion | A new bank/e-wallet app is installed on the device | Install e.g. Boost after Sciuro is already set up | A one-tap suggestion appears offering to track the newly installed app | Low | B (automation) | Not Tested
PAR-01 | Parsing | CIMB — DuitNow QR | CIMB DuitNow QR payment parses correctly | A real CIMB DuitNow QR notification exists | Let the notification be parsed | Amount, merchant, and channel (DuitNow QR) are all correctly extracted | Critical | A3 | Not Tested
PAR-02 | Parsing | Maybank — FPX | Maybank FPX payment parses correctly | A real Maybank FPX notification exists | Let the notification be parsed | Amount, merchant, and channel (FPX) are correctly extracted | Critical | A3 | Not Tested
PAR-03 | Parsing | BSN — standard transaction | BSN transaction parses correctly | A real BSN notification exists | Let the notification be parsed | Amount and direction are correctly extracted at minimum; channel where determinable | Critical | A3 | Not Tested
PAR-04 | Parsing | ATM withdrawal channel | ATM withdrawal is correctly channel-tagged | A real ATM withdrawal notification exists | Let the notification be parsed | Channel is tagged ATM_WITHDRAWAL, distinct from a normal card spend | Critical | A3 | Not Tested
PAR-05 | Parsing | Bahasa Malaysia variant | BM-language notification parses as accurately as English | Device/app locale set to Bahasa Malaysia for one bank | Trigger a transaction with the BM notification variant | Amount, direction, and channel extract correctly, matching English-variant accuracy | High | A3 | Not Tested
PAR-06 | Parsing | Graceful degradation | Unparseable format still books with partial data | A notification format the parser doesn't recognize (simulate if needed) | Let an unrecognized-format notification arrive | Transaction still books with at least the amount extracted and routes to Review Inbox rather than being dropped or crashing | Critical | A3/A4 | Not Tested
PAR-07 | Parsing | LLM fallback trigger | LLM extraction engages when regex fails | LLM-assisted parsing enabled in Settings; an unrecognized format arrives | Let the fallback path run | LLM extraction attempt occurs and produces a structured draft, visible in the transaction's extraction method | High | A4 | Not Tested
PAR-08 | Parsing | Available balance extraction | Avail Bal figure is captured where present | A notification containing an available-balance figure | Let it be parsed | The balance figure is correctly extracted and available to the reconciliation engine | High | A3 | Not Tested
CAT-01 | Triage & Categorization | Spend triage | Genuine purchase is triaged as SPEND | A normal merchant purchase notification | Let it be triaged | Transaction is tagged legType = SPEND, not TRANSFER or INCOME | Critical | A6 | Not Tested
CAT-02 | Triage & Categorization | Income triage | Genuine income is triaged as INCOME | A salary/allowance credit notification | Let it be triaged | Transaction is tagged legType = INCOME | Critical | A6 | Not Tested
CAT-03 | Triage & Categorization | Transfer triage | Self-transfer is triaged as TRANSFER, not spend | A DuitNow transfer to your own second account | Let it be triaged | Transaction is tagged legType = TRANSFER and excluded from spend categorization | Critical | A6/B2 | Not Tested
CAT-04 | Triage & Categorization | New merchant routing | First-time merchant routes to Review at low confidence | A transaction from a merchant never seen before | Let it be categorized | Transaction appears in Review Inbox rather than being silently auto-categorized incorrectly | High | A6 | Not Tested
CAT-05 | Triage & Categorization | Merchant memory | Repeat merchant auto-categorizes without review | A merchant confirmed once already in Review Inbox | A second transaction from the same merchant arrives | It is auto-categorized correctly without appearing in Review Inbox again | High | A6 | Not Tested
CAT-06 | Triage & Categorization | Manual recategorization | Editing a category from Transaction Detail works | Any confirmed transaction | Open Transaction Detail and change its category | Category updates immediately and an AuditLog entry records the change | Critical | A6 | Not Tested
TRF-01 | Transfer Detection | Bank-to-bank matching | Self-transfer between two banks auto-matches | Transfer sent between two of your own linked accounts | Let both notifications arrive | A single TransferLink is created; neither leg appears as spend or income | Critical | B2 | Not Tested
TRF-02 | Transfer Detection | ATM auto-credit | ATM withdrawal auto-credits the Cash wallet | An ATM withdrawal notification | Let it be processed | Cash wallet balance increases by the withdrawn amount with no manual confirmation needed | Critical | B2 | Not Tested
TRF-03 | Transfer Detection | Cash deposit confirm | Cash deposit prompts a one-tap confirm and debits Cash | A cash deposit notification | Let it be processed, then respond to the prompt | Cash wallet balance decreases by the deposited amount once confirmed | High | B2 | Not Tested
TRF-04 | Transfer Detection | Unmatched transfer routing | Unrecognized DuitNow Transfer recipient routes to Review | A transfer to a new, unrecognized recipient | Let it be processed | It appears in Review Inbox with a 'this is me / someone else' choice rather than being auto-classified | Critical | B2 | Not Tested
TRF-05 | Transfer Detection | Recipient learning | Confirming a recipient once teaches the rule | A recipient confirmed as 'me' in Review Inbox previously | A second transfer to the same recipient arrives | It auto-matches without prompting again | High | B2 | Not Tested
TRF-06 | Transfer Detection | Budget exclusion | Matched transfers never appear in budget totals | A confirmed TransferLink exists this month | Check Category Drilldown and Budgets screens | Neither leg of the transfer contributes to any category spend total | Critical | B2/B7 | Not Tested
CSH-01 | Physical Cash Wallet | Balance initialization | Cash balance starts correctly at first use | Fresh install, no cash activity yet | Open the Wallet screen | Balance shows zero with the correct empty state, not an error | Medium | B2 | Not Tested
CSH-02 | Physical Cash Wallet | Manual spend logging | Logging a cash spend updates the balance | Cash balance is nonzero | Use the 'Log cash spend' quick action with an amount | Cash balance decreases by that amount immediately | Medium | B2 | Not Tested
CSH-03 | Physical Cash Wallet | Recount flow | Recount shows correct computed-vs-actual variance | Cash balance has some value from prior activity | Run Recount Cash and enter a different actual amount | The variance is shown accurately and live as the amount is entered | High | B2 | Not Tested
CSH-04 | Physical Cash Wallet | Adjustment logging | Recount variance logs as an Adjustment with remark, not a spend category | A recount reveals a shortage or surplus | Complete the recount with a remark | A CashAdjustment entry appears in the Adjustments log; no spend category total changes | Critical | B2 | Not Tested
CSH-05 | Physical Cash Wallet | Multi-transaction accuracy | Cash balance stays accurate across a mix of ATM/deposit/spend activity | Several ATM withdrawals, one deposit, and a couple of logged spends have occurred | Compare computed balance to actual wallet cash | Balance matches within expected drift, and any gap is explainable via the Adjustments log | High | B2 | Not Tested
EWL-01 | E-Wallet Accounts | TNG capture | Touch 'n Go eWallet notification is captured and parsed | TNG eWallet installed and allowlisted | Trigger a TNG transaction | Transaction is captured, parsed, and appears against the TNG e-wallet account | Critical | A2/A3 | Not Tested
EWL-02 | E-Wallet Accounts | Other wallets capture | GrabPay, Boost, and ShopeePay notifications are captured | Each app installed and allowlisted | Trigger a transaction on each | Each is captured and parsed correctly, same as TNG | High | A2/A3 | Not Tested
EWL-03 | E-Wallet Accounts | Reload transfer linking | Bank-to-e-wallet reload creates a complete TransferLink | A reload from a bank account to an e-wallet | Let both notifications arrive | A TransferLink connects the bank debit and the e-wallet credit; neither shows as spend | High | B2 | Not Tested
EWL-04 | E-Wallet Accounts | E-wallet spend categorization | E-wallet spend categorizes like any normal transaction | An e-wallet purchase (e.g. GrabPay ride) | Let it be processed | It's categorized under the correct taxonomy category, same pipeline as bank spend | High | A6 | Not Tested
EWL-05 | E-Wallet Accounts | Cashback as income | E-wallet cashback/rewards book as passive income | A cashback credit notification from an e-wallet | Let it be processed | It's tagged as Income (Passive/other), not as a transfer or spend | Medium | A6 | Not Tested
OBL-01 | Recurring Obligations | Auto-detection | New recurring bill is proposed after repeated occurrences | The same merchant/amount/cadence has occurred 2-3 times (e.g. mobile plan) | Let the pattern repeat the required number of times | A 'looks like a new bill' proposal appears | High | B1 | Not Tested
OBL-02 | Recurring Obligations | One-tap confirm | Confirming the proposal creates a persistent obligation | A recurring obligation proposal is showing | Tap confirm | RecurringObligation is created and appears on the Kanban board | High | B1 | Not Tested
OBL-03 | Recurring Obligations | Cycle settlement | A matching new transaction settles the obligation cycle | An active RecurringObligation exists | The matching bill transaction arrives next cycle | status moves to PAID_THIS_CYCLE automatically, no manual action needed | Critical | B1 | Not Tested
OBL-04 | Recurring Obligations | Kanban linkage | Settlement moves the Kanban card correctly | An obligation just settled (OBL-03) | Open the Kanban board | The card has moved from Due Soon/Upcoming into Settled | Critical | B1/C1 | Not Tested
OBL-05 | Recurring Obligations | Amount drift handling | A single price change is flagged, a repeated one auto-updates | A subscription's amount changes for one cycle, then repeats at the new amount | Observe behavior across two cycles | First occurrence flags for review; after repeating, expectedAmount updates automatically | Medium | B1 | Not Tested
OBL-06 | Recurring Obligations | Manual editing | Editing an obligation's amount or date works correctly | An existing RecurringObligation | Edit its expected amount or day | Changes save and are reflected on the Kanban card and future detection | Medium | B1 | Not Tested
DBT-01 | Debt Ledger | PTPTN setup | PTPTN entry tracks balance, repayment, and due date correctly | A PTPTN debt entry is created (manually anchored) | View the Debt Overview | Balance, monthly repayment, and due date all display accurately | High | B5 | Not Tested
DBT-02 | Debt Ledger | Installment linkage | A loan installment notification reduces the linked debt balance | A Debt is linked to a RecurringObligation | The installment transaction arrives | Debt.outstandingBalance decreases by the installment amount automatically | Critical | B5 | Not Tested
DBT-03 | Debt Ledger | Credit card tracking | Credit card balance and due date track correctly | A credit card Debt entry exists | Make a purchase and a payment via card | Revolving balance and statement due date update accordingly | High | B5 | Not Tested
DBT-04 | Debt Ledger | Informal debt quick-add | Adding an informal debt is fast and minimal | On the Debt Ledger screen | Add an informal debt via the 3-field form (amount, counterparty, direction) | Entry saves correctly and appears in the debt list with no extra required fields | Medium | B5 | Not Tested
DBT-05 | Debt Ledger | BNPL risk flag | 3+ active BNPL plans trigger a risk flag | Three or more active BNPL installment plans exist | View Debt Overview | A visible risk indicator (StatusPill) appears, not a blocking alert | Medium | B5 | Not Tested
DBT-06 | Debt Ledger | Payoff celebration | A debt reaching zero balance triggers the celebration moment | A debt's final installment is about to be paid | Let the final installment post | outstandingBalance hits zero and the debt-payoff celebration (Lottie/haptic) fires once | Medium | B5/C | Not Tested
DBT-07 | Debt Ledger | Archive on payoff | A fully paid debt moves out of the active list | A debt was just paid off (DBT-06) | Return to Debt Overview | The paid-off debt no longer appears in the active list, and is bound to any 'paid off' history view | Low | B5 | Not Tested
BAL-01 | Balance & Reconciliation | Per-account accuracy | Running balance matches the real bank app | Normal transaction activity on one account over several days | Compare Sciuro's shown balance to the actual bank app | Balances match within a trivial margin | Critical | B3 | Not Tested
BAL-02 | Balance & Reconciliation | Drift detection | A missed notification triggers a drift flag | Simulate a gap (e.g. a transaction the app might have missed) | Let a subsequent Avail Bal figure arrive | A driftFlag is raised rather than silently showing a wrong balance | High | B3 | Not Tested
BAL-03 | Balance & Reconciliation | Cash reconciliation | Cash balance reconciles correctly after a recount | A recount was just completed | Check the Wallet balance | It matches the entered actual amount exactly, with the adjustment logged | High | B2/B3 | Not Tested
BAL-04 | Balance & Reconciliation | Transfer-driven balance update | Balances update immediately after a matched transfer | A transfer was just matched (TRF-01) | Check both accounts on Home | Both balances reflect the movement correctly and simultaneously | Critical | B2/B3 | Not Tested
INV-01 | Investment / Gold | Account creation | Gold Investment Account is created with correct starting weight | Setting up the Investment module for the first time | Add the Maybank GIA account with an initial weight | unitBalance reflects the entered starting weight in grams | High | B6 | Not Tested
INV-02 | Investment / Gold | Buy/sell entry | Manual buy/sell correctly adjusts the weight ledger | An existing InvestmentAccount | Log a buy of X grams, then a sell of Y grams | unitBalance updates correctly after each entry (never the MYR value directly) | High | B6 | Not Tested
INV-03 | Investment / Gold | Valuation calculation | Displayed value equals weight × current price | A known unitBalance and a known fetched gold price | Open the Investment screen | Displayed MYR value matches the manual calculation | High | B6 | Not Tested
INV-04 | Investment / Gold | Price refresh behavior | Value updates smoothly when the price refreshes | The Investment screen is open | Trigger a price refresh (reopen app or manual refresh) | The value count-animates to the new figure rather than jump-cutting | Medium | B6/C | Not Tested
INV-05 | Investment / Gold | Valuation disclaimer | The bank-spread caveat is visible | Any time the Investment screen is viewed | Open the Investment screen | A disclaimer noting the estimate may differ from Maybank's actual GIA rate is visible | Medium | B6 | Not Tested
BUD-01 | Budgeting | Manual limit setting | Setting a category budget limit works correctly | On the Budgets screen | Set a monthly limit for a category | Limit saves and progress tracks against it going forward | High | B7 | Not Tested
BUD-02 | Budgeting | Auto-suggested limits | A suggested limit appears once enough history exists | 2-3 months of category spend history exist | Open Budgets for an unset category | A suggested limit based on historical average appears, one-tap to accept | Medium | B7 | Not Tested
BUD-03 | Budgeting | 80% threshold | Crossing 80% of a budget triggers the correct state | A category is at or near 80% of its limit | Cross the threshold with a new transaction | The StatusPill/color state updates on both Budgets and Category Drilldown | High | B7 | Not Tested
BUD-04 | Budgeting | 100% threshold | Crossing 100% of a budget triggers the correct state | A category is at or over its limit | Cross the threshold | The state escalates correctly (and an opt-in notification fires if enabled) | High | B7 | Not Tested
BUD-05 | Budgeting | Transfer exclusion spot-check | Budget totals never include transfer-tagged transactions | A month with at least one self-transfer and normal spend | Review a category total against a manual sum of only true spend | The two match; the transfer amount is not included anywhere | Critical | B7 | Not Tested
AUD-01 | Audit Log | Creation logging | Every new transaction produces an AuditLog entry | Any new transaction is confirmed | Check its audit history | A CREATE entry exists with the correct source (SYSTEM_AUTO/LLM_INFERRED/USER_MANUAL) | Critical | A1 | Not Tested
AUD-02 | Audit Log | Change logging | Recategorizing a transaction logs a correct before/after entry | A transaction is recategorized (CAT-06) | Check its audit history | An UPDATE entry shows the old and new category with a timestamp | Critical | A1 | Not Tested
AUD-03 | Audit Log | Trail visibility | Audit history is viewable from Transaction Detail | Any transaction with at least one change | Open Transaction Detail and view history | Full change history displays in plain language, not raw JSON | High | A1/C | Not Tested
AUD-04 | Audit Log | Immutability | Audit entries cannot be edited or deleted after the fact | Any existing AuditLog entries | Attempt to alter history through normal app use | There is no path in the UI to edit or delete a past audit entry | Critical | A1 | Not Tested
AUD-05 | Audit Log | Source & confidence tagging | LLM-inferred actions are tagged with confidence | A transaction was categorized via LLM fallback | Check its audit entry | source = LLM_INFERRED with a populated confidence value | High | A1/A4 | Not Tested
CAS-01 | Cross-Module Cascades | Bill payment cascade | One bill payment updates Kanban, Budget, Runway, and Audit together | An active RecurringObligation with a matching transaction arriving | Let the matching transaction post | Kanban card settles, category budget increments, Home runway recalculates excluding it, and an audit entry is written — all without a second tap | Critical | B1/B7/C2 | Not Tested
CAS-02 | Cross-Module Cascades | Loan payment dual cascade | A loan installment updates both Debt and Kanban simultaneously | A Debt linked to a RecurringObligation, installment due | Let the installment transaction post | Debt balance decreases and the Kanban card settles from the same single event | Critical | B1/B5 | Not Tested
CAS-03 | Cross-Module Cascades | ATM cascade | ATM withdrawal cascades to Cash credit with zero manual steps | A card is used for an ATM withdrawal | Let the notification process | Cash wallet balance increases automatically; no confirmation prompt appears | Critical | B2 | Not Tested
CAS-04 | Cross-Module Cascades | Cash shortage isolation | A recount shortage corrects Cash balance without touching spend categories | A recount reveals a shortage | Complete the recount with a remark | Cash balance corrects; no category budget or spend total changes as a result | Critical | B2/B7 | Not Tested
CAS-05 | Cross-Module Cascades | Forward runway projection | Confirming a new obligation immediately affects future runway math | A new recurring obligation is confirmed (OBL-02) | Check Home's runway calculation for a date before the obligation's next due date | The obligation is now included in the forward projection without any extra setup | High | B1/C2 | Not Tested
CAS-06 | Cross-Module Cascades | Income timing inference | Recognized income pattern populates the runway's next-income date | A recurring income pattern (e.g. monthly stipend) has occurred 2-3 times | Check what date the runway calculation uses as 'next income' | The date reflects the detected pattern automatically, with no manual setup required | High | B3/C2 | Not Tested
NET-01 | Net Position | Aggregation accuracy | Net Position correctly sums all account types minus debt | Bank, cash, e-wallet, investment, and debt data all present | Compare the displayed Net Position to a manual sum | Figures match exactly | Medium | B7 | Not Tested
NET-02 | Net Position | Live recalculation | Net Position updates immediately when any input changes | Net Position is currently displayed | Make any change (new transaction, price refresh, debt payment) | The figure updates without needing to leave and reopen the screen | Medium | B7 | Not Tested
NET-03 | Net Position | Cross-check | Manually re-derived total matches what's shown, at any point in time | Any point with mixed account activity | Independently total every account/debt and compare | Sciuro's figure and the manual total agree | Low | B7 | Not Tested
REV-01 | Review Inbox | Low-confidence surfacing | Uncertain transactions appear in the Review Inbox | A transaction with low classification confidence exists | Open Review Inbox | The item is present with a suggested category shown | Critical | B4 | Not Tested
REV-02 | Review Inbox | Swipe confirm | Swiping resolves an item correctly | An item is pending in Review Inbox | Swipe to confirm the suggested (or a different) category | Item is categorized, removed from the inbox, and the merchant rule is learned | High | B4 | Not Tested
REV-03 | Review Inbox | Bulk re-categorize | Bulk re-categorizing by merchant works across items | Multiple pending items from the same merchant | Use bulk re-categorize for that merchant | All matching pending items resolve at once | Medium | B4 | Not Tested
REV-04 | Review Inbox | Empty state | Inbox shows the correct empty state when clear | No items pending | Open Review Inbox | A calm 'all caught up' empty state is shown, not a blank screen | Medium | B4 | Not Tested
REV-05 | Review Inbox | Duplicate handling | A likely duplicate transaction is flagged, not silently merged or doubled | Two very similar notifications arrive close together (simulating a pending-then-posted update) | Let both be processed | The duplicate is flagged for a decision rather than either double-counted or silently dropped | High | B4 | Not Tested
KAN-01 | Kanban Board | Column structure | Bills & Debt board shows the correct three columns | Any obligations/debts exist | Open the Kanban board | Upcoming, Due Soon, and Settled columns are all present and correctly populated | High | C1 | Not Tested
KAN-02 | Kanban Board | Auto-move on settlement | Bank-linked cards move automatically, no drag needed | An obligation just settled (OBL-04) | View the board | The card is in Settled without any manual drag | Critical | C1 | Not Tested
KAN-03 | Kanban Board | Manual move for informal debt | Informal debt cards require a manual settle action | An informal debt exists, marked as repaid in real life | Mark it settled manually | Card moves to Settled only after the manual tap, never automatically | Medium | C1 | Not Tested
KAN-04 | Kanban Board | Overdue surfacing | Overdue items are visually prioritized | An obligation has passed its due date unpaid | View the board | It surfaces at the top of Due Soon with a distinct visual treatment | High | C1 | Not Tested
KAN-05 | Kanban Board | Empty state | Board shows the correct state before any obligations exist | Fresh install, no detected obligations yet | Open the Kanban board | A passive empty state explains detection is still gathering data, with no premature 'add' prompt | Medium | C1 | Not Tested
HOM-01 | Home Dashboard | Runway calculation | Safe-to-spend figure calculates correctly against known data | A known balance and known set of upcoming obligations | Check the runway number against a manual calculation | Figures match | Critical | C2 | Not Tested
HOM-02 | Home Dashboard | Temperature indicator | Runway color reflects financial health accurately | Test at healthy, marginal, and low runway states | Observe the color at each state | Color moves calm to warning to danger appropriately and legibly | Medium | C2 | Not Tested
HOM-03 | Home Dashboard | Upcoming bills strip | Next 3 bills due are shown correctly | Multiple obligations with different due dates exist | View the Home screen | The three soonest-due items are listed in correct order | High | C2 | Not Tested
HOM-04 | Home Dashboard | Runway drilldown | Tapping the runway number opens an accurate breakdown | Runway figure is displayed | Tap the number | It expands to show exactly which obligations were subtracted | Medium | C2 | Not Tested
HOM-05 | Home Dashboard | Bill-to-Kanban handoff | Tapping a bill in the strip navigates correctly | A bill is visible in the upcoming strip | Tap it | Kanban opens pre-scrolled and highlighting that specific card | Medium | C2 | Not Tested
NAV-01 | Navigation & UI Shell | Nav structure | Bottom nav shows exactly 4 destinations plus a centered FAB | App is in normal use | Observe the bottom nav bar | Home, Kanban, Wallet, and More are present, with one centered elevated FAB, matching no more/fewer | Medium | C1-C3 | Not Tested
NAV-02 | Navigation & UI Shell | FAB quick-add | All quick-add actions function from the FAB | FAB is tapped | Select each quick-add option in turn (log cash, add informal debt, manual transaction) | Each opens the correct minimal-input flow and saves correctly | High | C1-C3 | Not Tested
NAV-03 | Navigation & UI Shell | Review Inbox is not a tab | Review Inbox never occupies a permanent nav slot | Review Inbox has pending items | Check the nav bar and the entry point used instead | It's absent from the tab bar; a banner/badge surfaces it only while non-empty | Medium | B4/C1 | Not Tested
NAV-04 | Navigation & UI Shell | No dead ends | Every core screen is reachable and returns cleanly | Normal app use | Navigate through every screen and back | No crashes, no dead-end screens, back navigation always works | Critical | C1-C3 | Not Tested
SEC-01 | Security | Encryption at rest | Local database is encrypted, not plaintext | App has real data stored | Attempt to inspect the raw database file directly | Contents are not human-readable without the encryption key | Critical | D1 | Not Tested
SEC-02 | Security | App gate | Biometric/PIN gate blocks unauthorized access | App lock is enabled | Attempt to open the app without authenticating | Access is blocked until authentication succeeds | Critical | D1 | Not Tested
SEC-03 | Security | Encrypted export | Manual backup export produces a usable, protected file | Some data exists to export | Trigger the export/backup flow | A file is produced, and it's encrypted (not a plain readable export) | High | D1 | Not Tested
SEC-04 | Security | No PII leakage | No personal/financial data appears in logs if analytics are enabled | Any analytics/crash reporting is active | Trigger a typical session and inspect any logs sent externally | No transaction text, amounts, or account identifiers appear | Critical | D1 | Not Tested
SEC-05 | Security | Raw text purge | Raw notification text purge option works as configured | Purge-after-N-days is enabled in Settings | Wait past the configured window (or simulate it) | Raw notification text is removed while structured transaction data remains intact | Medium | D1 | Not Tested
UIX-01 | Empty/Loading States | Empty states coverage | Every major screen has an appropriate first-use empty state | Fresh install or a screen with no data yet | Visit Home, Wallet, Investment, Kanban, Budgets, Debt Overview, Review Inbox in turn | Each shows a tailored, non-generic empty state rather than a blank or broken layout | Medium | B/C (per-module) | Not Tested
UIX-02 | Empty/Loading States | Skeleton loading | Cold loads show skeleton placeholders, not blank spinners | Cold app start with data to load | Open the app fresh | Shimmer/skeleton shapes matching the eventual layout appear briefly before real content | Medium | C1-C3 | Not Tested
UIX-03 | Empty/Loading States | Optimistic UI | One-tap confirms update instantly, not after a wait | Any one-tap confirm action (Review Inbox, mark bill settled) | Perform the action | UI updates immediately; the background save happens invisibly after | High | B4/C1-C3 | Not Tested
UIX-04 | Empty/Loading States | Sync freshness indicator | Background sync status is visible without being intrusive | Normal background notification processing is occurring | Check the Home header area | A subtle 'synced Xm ago' indicator is present and accurate, not a blocking spinner | Low | B3/C2 | Not Tested
UIX-05 | Empty/Loading States | Reduced motion respect | System reduced-motion setting disables Lottie/confetti correctly | OS-level reduced motion is enabled | Trigger a celebration moment (e.g. debt payoff) | A static fallback appears instead of the full animation, no crash or broken layout | Medium | C/D1 | Not Tested
SET-01 | Settings | Allowlist management | Adding/removing tracked apps works correctly | Settings > notification sources | Add or remove an app from the allowlist | Future notifications from that app are captured or ignored accordingly | High | A2/D1 | Not Tested
SET-02 | Settings | LLM opt-in toggle | Enabling/disabling LLM-assisted parsing works as expected | Settings > AI parsing | Toggle it off, then trigger a parse-fallback scenario | No external call is made while off; fallback resumes correctly once re-enabled | Critical | A4/D1 | Not Tested
SET-03 | Settings | Appearance setting | Light/Dark/System selection applies across the whole app | Settings > Appearance | Switch between all three options | Every screen updates consistently, no screens left in the wrong theme | Medium | D1 | Not Tested
SET-04 | Settings | Backup trigger | Manual export/backup completes and includes expected data | Settings > Backup | Trigger an export | A complete, correct file is produced covering all modules (not just transactions) | High | D1 | Not Tested
DSK-01 | Desktop Companion | Read-only sync view | Windows desktop viewer displays synced data correctly | Desktop companion is set up and synced | Open the desktop app | Balances, obligations, and recent activity match the phone, view-only | Low | Deferred/Future | Not Tested
DSK-02 | Desktop Companion | Lottie fallback on desktop | Desktop correctly falls back where Lottie doesn't render | A moment that uses Lottie on Android (e.g. empty state) | View the equivalent screen on desktop | A static image appears in place of the animation, no error or blank space | Low | Deferred/Future | Not Tested